Tayseer Al-rahman Zoom App

Work Breakdown Structure (WBS)

Project Overview

Project: Video Meeting Mobile App (Zoom-like)
Duration: 1 Month (4 Weeks)
Frontend: Flutter (Web & Android)
Tech Stack:

Frontend: Flutter

Backend:

- Video & Conferencing: Jitsi Meet (Flutter SDK)

- API: Node.js (Express.js)

- Database: MongoDB (users) & Firebase (meetings metadata)

- Real-time / Signaling: Handled by Jitsi infrastructure

- Hosting: Android: (Google Play Store) / Web: (Netlify+Heroku)

1. Planning & Requirements (Week 1)

1.1 Define project scope & assumptions DONE
1.2 Finalize user stories

1.3 Define MVP features

  - Technical architecture design

- Frontend–backend interaction

- Auth flow

Deliverables:

- Finalized requirements document

- High-level architecture diagram

2. UI/UX Design (Week 1)

2.1 UX flow design

- Login flow

- Home screen

- Meeting screen

2.2 UI wireframes

- Login screen

- Home (meeting list / join)

- Video call screen

- Bottom navigation (5 buttons)

2.3 UI design system

- Color palette

- Typography

- Spacing & layout rules

Deliverables:

- Wireframes

3. Frontend Development – Flutter (Weeks 2–3)

3.1 Project setup

- Flutter project initialization

- Folder structure & routing

3.2 Authentication

- Google Sign-In integration

- Auth state handling

3.3 Core UI implementation

- Login page

- Home screen

- Bottom navigation (5 tabs)

- Infinite scrolling lists

3.4 Video meeting UI

- Video grid layout

- Mute / camera buttons

- Leave meeting button

3.5 State management

- Auth state

- Meeting state

Deliverables:

- Functional Flutter app

4. Backend Development (Weeks 2–3)

4.1 Backend project setup

- Folder structure & routing

- Express.js setup

- MongoDB setup

4.2 Authentication backend

- Firebase Auth integration

- User profile storage

4.4 Database design

- Users collection

- Meetings collection

Deliverables:

- Secure backend APIs

- Database schema (models)

5. Testing & QA (Week 4)

5.1 Functional testing

Login flow

Meeting creation/join

5.2 UI/UX testing

Spacing & responsiveness

Navigation flow

5.3 Performance testing

Call stability

Latency checks

5.4 Bug fixing

Deliverables:

- Bug-free MVP

- Test report

7. Deployment & Release (Week 4)

7.1 Backend deployment

- Cloud hosting setup

- Environment variables

7.2 Mobile build

- Android APK

- Web app (for IOS users)

7.3 Release readiness

Deliverables:

- Deployed backend

- Installable mobile app

8. Documentation & Handover (Week 4)

8.1 Technical documentation

- Architecture overview

- API documentation

8.2 User documentation

- App usage guide

8.3 Project handover

Deliverables:

- Complete documentation

- Final project handoff

Timeline Summary

- Week 1: Planning + UI/UX

- Week 2: Frontend & Backend foundation

- Week 3: Video calls & core features

- Week 4: Testing, deployment, documentation

Gantt Chart (1-Month Timeline)

| Task ID | Task Name | Week 1 | Week 2 | Week 3 | Week 4 |
| --- | --- | --- | --- | --- | --- |
| 1 | Planning & Requirements | █████ |  |  |  |
| 1.1 | Scope & User Stories | ███ |  |  |  |
| 1.2 | Architecture Design | ███ |  |  |  |
| 2 | UI/UX Design | █████ |  |  |  |
| 2.1 | UX Flows | ███ |  |  |  |
| 2.2 | Wireframes & UI System | ███ |  |  |  |
| 3 | Frontend (Flutter) |  | █████ | █████ |  |
| 3.1 | Project Setup |  | ███ |  |  |
| 3.2 | Auth & Navigation |  | ███ | ███ |  |
| 3.3 | Video Call UI |  |  | ███ |  |
| 4 | Backend Development |  | █████ | █████ |  |
| 4.1 | Backend Setup & Auth |  | ███ |  |  |
| 4.2 | Meeting APIs & DB |  | ███ | ███ |  |
| 5 | Video & Real-Time |  |  | █████ |  |
| 5.1 | WebRTC Integration |  |  | ███ |  |
| 5.2 | Signaling Server |  |  | ███ |  |
| 6 | Testing & QA |  |  |  | █████ |
| 6.1 | Functional & UI Testing |  |  |  | ███ |
| 6.2 | Bug Fixing |  |  |  | ███ |
| 7 | Deployment & Release |  |  |  | ███ |
| 8 | Documentation & Handover |  |  |  | ███ |

Legend: ███ = Partial effort | █████ = Primary focus

Project Outcome:
A clean, modern, Zoom-like video meeting mobile app MVP built with Flutter and a scalable backend, delivered within 1 month.